## Slide 1
Milestone | Due Date | Result
Select PCO (MECI) End | 12-26-2014 | 
December Press Release - Recap of prior work & Seasonal greetings End | 12-31-2014 | 
Announcement of Important dates of Call for Academic Papers/Workshops/General Presentations End | 01-12-2015 | 
Website able to accept proposals/Academic Track, Workshop, General Track End | 02-09-2015 | 
Send Call for Papers/Presentations/Workshops End | 02-23-2015 | 
Close Call for Workshops End | 03-23-2015 | Totally 32 Proposals submitted
Early bird sponsorship deadline End | 03-31-2015 | 
Decide and broadcast workshop selection End | 03-31-2015 | 
Workshop Schedule Release End | 04-09-2015 | 23 Proposals have accepted
Early Bird Registration Opens End | 04-09-2015 | 
Academic abstract submission deadline End | 05-15-2015 | Oral: 48 abstracts from 20 countries Poster: 18 abstracts from 7 countries
Regular Track presentation deadline End | 05-15-2015 | 180 descriptions from 33 countries
Begin community voting on presentations End | 05-25-2015 | 
Close community comments on presentations End | 06-05-2015 | 
Presentation Selection End | 06-15-2015 | 164 descriptions have accepted among 180 descriptions
Academic Track Review Decisions End | 06-15-2015 | Oral: 36 abstracts have accepted among 48 abstracts Poster: include 12 abstracts which has not accepted on oral session, totally 30 abstracts have accepted
Early Bird Registration Discount Ends End | 06-22-2015 | 240 registrants from 32 countries
Preliminary program decisions made & posted End | 06-29-2015 | 
Exhibitor Manuals distributed to all sponsors End | 07-17-2015 | 
Online Registration Ends End | 09-02-2015 | Including Early Bird Registrants, 473 registrants from 39 countries
Conference Begins End | 09-14-2015 | Including On-site Registrants, Totally, 563 registrants from 48 countries (International: 309, Domestic: 254)
Milestone